## Read
Porject Title: |  | <Electroencephalogram Headset for BCI Applications_TTS>
No | Student Name ( First, Last ) | email | Faculty (First, Last) | email
1 | Thang Pham | thangp@usf.edu | Ashwin Parthasarathy | ashwinbp@usf.edu
2 | Shovan Shakya | shovanshakya@usf.edu
3 | Tristan Valenzuela | valenzuela1@usf.edu
4
Please DO NOT change the format of this template
For any update or changes instructor will provide update to the template, as deemed necessary.
File Name should be : Project Name Titles_Last Names or initials of team members
This report is cumaltive, and you should add/update this and submit to canvas. Add extension to it to align with the report number due.
Please work with your team member(s) to update this and weekly basis, the purpose of this sheet is to keep all team members aligned and up to date.

## Action Register
Minimum one action item per team member per week | [7 empty] | Provide short status in a bulletize forms Closure plans? Why delay?
# | Date Created | Originator | Description | Assignee | Original Due Date | Status | Updated Due Date | Status and Closure Comments | Aging
1 | 2024-01-27 | Tristan | Reach out to Dr. Ashwin and schedule a periodic meeting. | Tristan | 2024-01-27 | Closed | 2024-01-27 | Successfully reached out to Dr. Ashwin. Scheduled meeting time is every Monday at 3 PM.
2 | 2024-01-27 | Shovan | Research DSP techniques for EEG. | Shovan | 2024-01-27 | Open | 2024-01-27 |  | 0
3 | 2024-01-27 | Thang | Finish documenting the created UART system for the project. | Thang | 2024-01-27 | Open | 2024-01-27 |  | 0
4 | 2024-01-28 | Tristan | Research Right-Leg-Drive system for EEG systems. | Tristan | 2024-01-28 | Open | 2024-01-30
5 |  |  | SRD documents
6 |  |  | Meet Faculty advisor
7 |  |  | PDR preperation
8 |  |  | Meeting to prep for PDR
9 |  |  | WBS development
10 |  |  | Schedule development
11 |  |  | Establish Bill of material
12 |  |  | Arrange Meeting with faculty advisor
13 |  |  | Establish weekly teleconference/meeting
14
Add more as needed and according to your project

## Accomplishments
Tri-Weekly status. The content of the weekly communication is: a) Program schedule, technical and cost status b) Significant accomplishments c) Issues and resolution plans d) Action items status e) Provide date and time of meeting with the advisor The purpose of this document is for the individual function Team/leads to provide current status in their specific area to be included in the project status Need to provide progress against, at minimum: SRD, SRR, PDR, Website, schedule, WBS, BOM etc.
This Column tracks your significant accomplishments. You can use this to sub-tasks from your scheduled progress.
# | Week of Accomplishments | Description of Accomplishment | Notes
1 | 2018-01-11 | e.g., Meet with the team to coordinate new product development | What was achived? Is it done or needs more work? If yes, was the action assigned to a team member?
2
3
4
5
6

## Project Schedule
This is notional template and dates need to alighn with class desginated dates and deadlines. As a team you need to further break down class deadlines to keep your team on track
| Desing I | [16 empty] | Design II - subject to change per design II Intructor
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33
Needs to Align with Instructors deadlines
Intructors Milestones
[11 empty] | SRD due |  |  |  |  | PDR |  |  |  | CDR | [11 empty] | Design Demonstration
Team Formation and Advisor established
WBS, Org. and Schedule due, embeded in excel
Requirements Doc Due ( Preliminary & Final )
Final Document Package due
Team/Student needs to provide further schedule detial to accomplish the tasks | [33 empty] | < Please modify this section of schedule per your project
Planning and Systems Engineering
Product Idea/Concept
System Engineering Managent Plan
System Requirements Document (SRD)
Design Document
Major Design Deadlines | Design II - subject to change per design II Intructor 22: Procure
Design, Procure, Build, & Test | Design II - subject to change per design II Intructor 18: Design; Design II - subject to change per design II Intructor 25: Build; Design II - subject to change per design II Intructor 31: Test
Sub Design and Development Tasks
Sub task 01
Sub task 02
Sub task 03
Sub task 04
Assumptions:
1. List critical schedule assumptions, dependcies

## WBS
Team | Need to break down task so a single individual is responsible. For example, EE task can be broken for two individuals or more, as needed | By writing this, team member agrees to the task assignment | By writing this, team member agrees to the task assignment
Roles | Responsible Individual | TASK DESCRIPTION - Design I | TASK DESCRIPTION - Design II
MANAGEMENT
Technical Leader | Student 1 | write the perceived detail | write the perceived detail
Team Coordination Leader | Student 2
Cost & Schedule leader | Student 3
SYSTEM ENGINEERING
SYST ENGINEERING | Student 1 | Example: SEMP Document
SYST ENGINEERING | Student 3 | Example: Requirements Documents
TEST ENGINEERING | Student 2
PROD ENGINEERING | Student 3
CONFIG MGMT | Student 1
RELIABILITY | Student 2
QUALITY | Student 3
PARTS MANAGEMENT | Student 1
EMI / EMC | Student 2
SAFETY | Student 3
Hardware
ELECT.DESIGN
DESIGN | Student 1
MECH. DESIGN
PSNA DESIGN | Student 2
SOFTWARE
SW DEVELOPM | Student 3
TEST Engineering
Test | Student 3
TEST SOFTWARE
DESIGN | Student 2

## BOM
Index | Component Name | Short description | function, how it is used in your system | Quantity | Cost | Reference or links to websites
1
2