## Read
Porject Title: |  | <Electroencephalogram Headset for BCI Applications_TTS>
No | Student Name ( First, Last ) | email | Faculty (First, Last) | email
1 | Thang Pham | thangp@usf.edu | Ashwin Parthasarathy | ashwinbp@usf.edu
2 | Shovan Shakya | shovanshakya@usf.edu
3 | Tristan Valenzuela | valenzuela1@usf.edu
4
Please DO NOT change the format of this template
For any update or changes instructor will provide update to the template, as deemed necessary.
File Name should be : Project Name Titles_Last Names or initials of team members
This report is cumaltive, and you should add/update this and submit to canvas. Add extension to it to align with the report number due.
Please work with your team member(s) to update this and weekly basis, the purpose of this sheet is to keep all team members aligned and up to date.

## Action Register
Minimum one action item per team member per week | [7 empty] | Provide short status in a bulletize forms Closure plans? Why delay?
# | Date Created | Originator | Description | Assignee | Original Due Date | Status | Updated Due Date | Status and Closure Comments | Aging
1 |  |  | SRD documents | [5 empty] | 0
2 | 2024-01-27 | Tristan | Meet Faculty advisor | Tristan | 2024-02-06 | Closed |  | Met with Faculty advisor and established a task. | 0
3 |  |  | PDR preperation | [5 empty] | 0
4 |  |  | Meeting to prep for PDR | [5 empty] | 0
5 | 2024-02-18 | Tristan | WBS development | Shovan | 2024-02-18 | Closed |  | Held a meeting and discussed roles. | 0
6 |  |  | Schedule development | [5 empty] | 0
7 |  |  | Establish Bill of material | [5 empty] | 0
8 | 2024-02-01 | Shovan | Arrange Meeting with faculty advisor | Thang | 2024-02-06 | Closed |  | Met with faculty advisor and established a weekly meeting schedule. | 0
9 | 2024-02-01 | Shovan | Establish weekly teleconference/meeting | Thang | 2024-02-06 | Closed |  | Met with faculty advisor and established a weekly meeting schedule. | 0
Additional | [8 empty] | 0
10 | 2024-01-27 | Tristan | Reach out to Dr. Ashwin and schedule a periodic meeting. | Tristan | 2024-01-27 | Closed | 2024-01-27 | Successfully reached out to Dr. Ashwin. Scheduled meeting time is every Monday at 3 PM. | 0
11 | 2024-01-27 | Shovan | Research DSP techniques for FNIRS. | Shovan | 2024-01-27 | Closed | 2024-01-27 | Looked into research papers and other documentation. Wrote into Github. | 0
12 | 2024-01-27 | Thang | Finish documenting the created UART system for the project. | Thang | 2024-01-27 | Closed | 2024-01-27 | Documentation of the UART system is on Github. | 0
13 | 2024-01-28 | Tristan | Research LED Driving system for fNIRS systems. | Tristan | 2024-01-28 | Closed | 2/30/2024 | Gathered sufficient information regarding LED Sensor system to begin project. | 0
14 | 2024-02-18 | Tristan | Research LED sensor system (Transconductance Amplifier etc.) | Tristan | 2/30/2024 | Closed | 2/30/2024 | Gathered sufficient information regarding LED Sensor system to begin project. | 0
15 | 2024-02-18 | Thang | Research STM32 MCU. | Thang | 2/30/24 | Open | 2024-05-01 | There is still a lot to learn about the STM32. What is needed to know increases due to new requirements for the project being made. | 0
16 | 2024-03-18 | Tristan | Research Hardware Design for STM32F7 | Tristan | 2024-03-22 | Open | 2024-03-22 |  | 0
17 | 2024-03-18 | Tristan | Create schematic block diagram for both MCU and Source-Detector systems. | Tristan | 2024-03-22 | Open | 2024-03-22 |  | 0
18 | 2024-03-18 | Thang | Research the ADC on the STM32F7 board. | Thang, Tristan, Shovan | 2024-04-18 | Open | 2024-04-18 |  | 0
19 | 2024-03-18 | Thang | Research how to implement RTOS. | Thang, Shovan, Tristan | 2024-05-02 | Open | 2024-05-02 |  | 0
20 | 2024-03-18 | Shovan | Research flexible PCB | Shovan, Tristan | 2024-03-22 | Open | 2024-03-22 |  | 0
21 | 2024-03-18 | Shovan | Research flexible material for headband | Shovan, Tristan | 2024-04-08 | Open | 2024-04-08 |  | 0
22 | [8 empty] | 0
23 | [8 empty] | 0
24 | [8 empty] | 0
25 | [8 empty] | 0

## Accomplishments
Tri-Weekly status. The content of the weekly communication is: a) Program schedule, technical and cost status b) Significant accomplishments c) Issues and resolution plans d) Action items status e) Provide date and time of meeting with the advisor The purpose of this document is for the individual function Team/leads to provide current status in their specific area to be included in the project status Need to provide progress against, at minimum: SRD, SRR, PDR, Website, schedule, WBS, BOM etc.
This Column tracks your significant accomplishments. You can use this to sub-tasks from your scheduled progress.
# | Week of Accomplishments | Description of Accomplishment | Notes
1 | 2024-01-15 | We formed our group and scheduled a weekly meeting time with our sponsor and advisor. | The meeting time we decided on was every Monday @ 3 PM.
2 | 2024-01-22 | Met with our sponsor Dr. Ashwin at 3 PM and discussed our project's scope. | We are given a choice in between doing EEG or fNIRS.
3 | 2024-01-29 | Met with our sponsor Dr. Ashwin at 3 PM and updated him on our decision to go with fNIRS. | We discussed different academic research papers aimed to determine the feasibility of BCI applications with fNIRS.
4 | 2024-02-05 | We were able to narrow down feasible BCI applications with fNIRS, and reported our findings to our sponsor. | We narrowed down feasible BCI applications to be passive BCI applications. We discussed potential research such as using fNIRS to determine a shift in concentration during a gaming session from distractions.
5 | 2024-02-12 | We successfully came up with a starting hardware block diagram and pitched it to our sponsor.
6 | 2024-02-19 | We further fleshed out the specifications for the hardware. | We made progress in piecing together the sensor mechanism of fNIRS.
| 2024-03-18 | Completed preliminary SRD

## Project Schedule
This is notional template and dates need to alighn with class desginated dates and deadlines. As a team you need to further break down class deadlines to keep your team on track
| Design I | [16 empty] | Design II - subject to change per design II Intructor
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33
Needs to Align with Instructors deadlines
Intructors Milestones
[11 empty] | SRD due |  |  |  |  | PDR |  |  |  | CDR | [11 empty] | Design Demonstration
Team Formation and Advisor established
WBS, Org. and Schedule due, embeded in excel
Requirements Doc Due ( Preliminary & Final )
Final Document Package due
Team/Student needs to provide further schedule detial to accomplish the tasks | [33 empty] | < Please modify this section of schedule per your project
Planning and Systems Engineering
Product Idea/Concept
System Engineering Managent Plan
System Requirements Document (SRD)
Design Document
Major Design Deadlines | Design II - subject to change per design II Intructor 22: Procure
Design, Procure, Build, & Test | Design II - subject to change per design II Intructor 18: Design; Design II - subject to change per design II Intructor 25: Build; Design II - subject to change per design II Intructor 31: Test
Sub Design and Development Tasks
Hardware Design
Software Implementation
First Prototype
Revision
Assumptions:
1. First prototype works

## WBS
Team | Need to break down task so a single individual is responsible. For example, EE task can be broken for two individuals or more, as needed | By writing this, team member agrees to the task assignment | By writing this, team member agrees to the task assignment
Roles | Responsible Individual | TASK DESCRIPTION - Design I | TASK DESCRIPTION - Design II
MANAGEMENT
Technical Leader | Tristan | Ensure system requirements and documentation are up to date and accurate. Lead the technical aspects of the project such as design, testing, and integration.
Team Coordination Leader (scrum master) | Thang | Hold weekly meetings, make meeting minutes
Cost & Schedule leader | Shovan | Make sure project materials does not exceed budget. Order and find parts that fit the financial contraints
SYSTEM ENGINEERING
SYST ENGINEERING | Shovan | Example: SEMP Document
SYST ENGINEERING | Tristan | Requirements documentation (SRD)
TEST ENGINEERING | Thang | Ensure that the system is integrated together properly and is functional.
PROD ENGINEERING | Tristan |  | Overlook prototype and ensure production step is feasible
CONFIG MGMT | Shovan
RELIABILITY | Tristan |  | Perform reliability analysis of final design
QUALITY | Thang | Ensure that the developed system meets predefined metrics.
PARTS MANAGEMENT | Thang | Ensure that the components picked for the system are sensible and documented.
EMI / EMC | Tristan |  | Ensure design meets EMI/EMC responsibilities
SAFETY | Shovan |  | Make sure device does not emit harmful or overpowered signals. Make sure device is comfortable and does not cause user harm
Hardware
ELECT.DESIGN | Tristan | Design hardware system and CCAs
Shovan
| Thang | Determine the hardware components (such as MCUs) that the software will be developed on.
DESIGN | Tristan | Design 3D-printed assemblies.
Shovan
Thang
MECH. DESIGN
PSNA DESIGN | Tristan
SOFTWARE
SW DEVELOPM | Thang | Write software for the microcontroller and PC interface.
Shovan
Tristan
TEST Engineering
Test | Shovan
TEST SOFTWARE
DESIGN | Thang | Develop unit tests to ensure software robustness.

## BOM
Index | Component Name | Short description | function, how it is used in your system | Quantity | Cost | Reference or links to websites
1
2